create all new DB tables
database-changes-for-units
Analyze & choose graph package
Partly complete
In progress/assigned
Create graph from units & conversions DB tables
creating-graph
Create models to interface to DB changes
model-changes-for-units
automated input of example units and conversions
figure out how to get readings
database-changes-for-units
Implement conversion functions
determining-conversions
Create unit with suffix functions/code
later in determining-conversions
Transfer Pik on client arrival
test conversions including temperature
determining-conversions
test Cij/Pik creation
determining-conversions
Implement compatible units functions
determining-compatible-units
new SQL function(s) to get meter graphic readings
meter-graphic-values
new SQL function(s) to get group graphic readings
group-graphic-values
analyze bar/compare/map graphics for any needed changes
bar-compare-map-graphic-values
y-axis label
graphs
Able to do line graph
Create data and tests for the simplified examples in text
Probably done earlier while developing code
Able to do bar/compare/map
 graph
design and implement tests for each function/code in text
Mostly done as each set are completed
chart link feature
chartlink
create DB migrations
database-changes-for-units
new SQL function to get rate data
how-oed-should-calculate-readings-displayed-in-line-graphics
create standard units for input into OED
database-changes-for-units
auto created meters
autocreated-meters
 completion needed to begin
Desirable to do
Task needed to finish
design//stubs needed to begin
UI dependent on compatible units
meters & groups menus
changes-to-meters-groups-dropdown-menus
group viewing page
group-viewing-pages
meter viewing page
meter-viewing-page
units menu
new-units-menu
Features dependent on DB changes
export feature
export
csv upload page
Zcsv-upload-page
Features dependent on DB changes
admin unit page
new-admin-unit-page
admin conversion page
Znew-admin-conversion-page
completed
design/stubs done